## 23rd Dec 2016
S.No | Task | Priority | Remarks | Status on 23rd Dec 2016 | Production Timeline
1 | Export to Excel | 1 | Optimizing the queries. Will be completed by Tuesday i.e. 25th Oct 2016 | Completed. | 13th Dec 2016
5 | Synonyms to be included in search | 1 | To be discussed with SME and finalize the implementation. | InProgress | Need to finalize
6 | Keyword search | 1 | In progress . We will let you know the timeline. | Completed and released for internal tesing. | 29th DEC 2016
10 | Single module export to Pdf | 2 |  | Completed. | 24th Dec 2016
14 | Data back up and upload to cloud | 1 | Requirement finalized on 11th Nov 2016 | Checking for the other alternatives.
15 | Testing in Cloud Server (test server) | 1 | Requirement finalized on 11th Nov 2016 | Checking for the other alternatives. | depends on the IT Team support for Latency issues
16 | Make Live | 1 | Requirement finalized on 11th Nov 2016 | Checking for the other alternatives.
23 | Drop Downs : will need third party open source application to be integrated ; | 1 | Requirement finalized on 9th Nov 2016 |  | 24th Dec 2016
24 | Molecule Images : High Resolution Images from PubMed to be available by 12/Nov | 2 | Requirement finalized on 9th Nov 2016 | PubMed Webservice calling issue. Working on it. | 18th Dec 2016
26 | MAP : to study multiple options // till that improve on the heading of MAP | 2 | Requirement finalized on 11th Nov 2016
28 | Jquery tables implementation for increasing application performance in all the modules | 1 | Completed. Internal testing is in progress and will be completed by 8th Dec 2016. | Internal testing is completed and fixing reported issues. | 24th Dec 2016
30 | 3D charts in Product snapshot by Theraphy area/Phase | 1 | Getting issue while converting to 3D. Checking the issue. | Working on it. Will be completed by 19th Dec 2016 | 24th Dec 2016
35 | LogOff/No Network data capturing | 2 | Need to finalize the requirement. | Once priority tasks are completed, need to discuss on this
36 | Include Subsidiries - Parent should be on top | 2 |  | Need to change the DB procedure. No front end changes.
38 | Interactability Charts | 2 | Products by Highest Phase is completed. Working on other charts. | Products by Highest Phase is completed. Working on other charts.
40 | Subscription Report format | 2 | Working on it. Renamed as User Dasboard. Req. 47
43 | Regulatory pdf download option | 2 | Need to transfer Regulatory pdf files to Cloud server and provide download option. | Will be completed by 13th Dec 2016. | 13th Dec 2016
44 | Blog like interface for Whitepapers | 1 | Request raised on 5th Dec 2016. Checking the feasibility.
45 | Convert Pie to Bar chart in Events | 1 |  | Kept on hold because of the other priority tasks. Will be completed by 19th Dec 2016 | 24th Dec 2016
47 | User DashBoard | 2 | Request raised on 8th Dec 2016. | InProgress | 24th Dec 2016
48 | Company Snapshot | 1 | Whereever company name is displaying in the grid, there should be an hyperlink for the company name to show Company Snapshot. | Internal testing is completed. | 24th Dec 2016
49 | Regulatory Snapshot in Patents Single view | 1 | In the Regulatory Information tab, redirecting to Regulatory Single View if user clicks on View. There should an popup to display Regulatory Information. | Internal testing is completed. | 24th Dec 2016
51 | Patent and Exclusive details addtion in Regulatory Single View | 1 | Request raised on 8th Dec 2016. Need to finalize it. | Internal testing is completed. | 24th Dec 2016
52 | Pdf report Last Page with Modules and Contact Info | 1 |  | Completed. Only interactivity on social n/w sites are pending. | 24th Dec 2016
53 | Companies Info display (without login) | 2 | Request raised on 8th Dec 2016. Need to finalize it.
54 | Separate Home page for each module | 2 | Request raised on 9th Dec 2016. Need to finalize it.
55 | Maintenance page | 1 | Request raised on 14th Dec 2016. | Completed. | 24th Dec 2016
56 | Email Alerts | 1 | Request raised on 16th Dec 2016 | Need to finalize the requirement

## Raju Requirements
S.No | Task | Priority | Remarks | Status on 23rd Dec 2016 | Production Timeline
20 | 3D change to be implemented by Raju and share with Team. | 1 | Requirement finalized on 10th Nov 2016 | Completed and moved to live site. | 14th Nov 2016
21 | Headings to be made outline / more beautiful | 1 | Requirement finalized on 11th Nov 2016 | Completed and moved to live site.
22 | Basic Search : all module search headings : beautification along-with icon as discussed | 1 | Requirement finalized on 10th Nov 2016 | Completed and moved to live site. | 22nd Nov 2016
23 | Drop Downs : will need third party open source application to be integrated | 1 | Requirement finalized on 9th Nov 2016 | Completed. Will be published on 24th Dec 2016 | 24th Dec 2016
25 | Company Logos : High Resolution Images to be used. | 2 | Requirement finalized on 10th Nov 2016 | Completed and moved to live site. | 22nd Nov 2016
26 | MAP : to study multiple options // till that improve on the heading of MAP | 2 | Requirement finalized on 11th Nov 2016 | Working on it.
28 | Dropdown default values and place holder/tooltip in the textbox controls in all search modules. | 1 |  | Completed and moved to live site on 30th Nov 2016 | 25th Nov 2016
39 | White papers integration | 1 |  |  | 2nd Dec 2016
30 | 3D charts in Product snapshot by Theraphy area/Phase | 1 | Getting issue while converting to 3D. Checking the issue. | Completed. Will be published on 24th Dec 2016 | 24th Dec 2016
44 | Blog like interface for Whitepapers | 1 | Request raised on 5th Dec 2016. Checking the feasibility. | Checking the popup functionality feasibility checking.
52 | Pdf report Last Page with Modules and Contact Info | 1 | Design is in progress | InProgress | 19th Dec 2016
55 | Maintenance Page UI design |  |  | Completed. Will be published on 24th Dec 2016 | 24th Dec 2016

## CompletedTasks
S.No | Task | Priority | Dev. Timeline | Remarks | Status on 11th Nov 2016 | Status on 23rd Nov 2016 | Production Timeline
2 | Logout Issue | 1 | 8th Nov 2016 |  | Will be moved to production on 14th Nov 2016 | Will be moved to production on 24th Nov 2016 | 11th Nov 2016
4 | Latest Data upload for all modules. | 1 | 4th Nov 2016 | Completed |  |  | Completed
7 | Regulatory tool | 1 | 19th Oct 2016 | Completed Patent mapping and Review classification. Released for testing. |  | Completed. | 9th Nov 2016
9 | SMTP integration | 2 | 26th Oct 2016 | SMTP integration is completed and getting mails from the myPharmaThinktank website. But mails are blocking by the SPAM manager. Need to discuss with IT team on this. |  |  | 11th Nov 2016
11 | Blog integration | 2 | 24th Oct 2016 | Development is in progress. | Integrated WordPress on Test link and provided access to Sanjay. Once we get the confirmation from him, we will move it to live server. | Got feedback from Sanjay Aikat on 17th Nov 2016 and moved to live on 23rd Nov 2016 | 23rd Nov 2016
12 | Writing SQL scripts | 1 |  | Requirement finalized on 11th Nov 2016 |  | Completed on 18th Nov 2016 | 14th to 18th Nov 2016
13 | Testing in local server | 1 |  | Requirement finalized on 11th Nov 2016 |  | Not done because of the demo companies data upload and other priority issues. | 21st Nov and 22nd Nov 2016
17 | Presently 22,000 out of 30,000 Patent PDFs extracted and need to upload to Cloud Server | 1 |  | Requirement finalized on 11th Nov 2016 | InProgress | Completed and moved all the patent pdf files to cloud server. | Completed on 29th Nov 2016
18 | Testing on local as well as on cloud test server | 1 |  | Requirement finalized on 11th Nov 2016
19 | Make Live on Cloud | 1 |  | Requirement finalized on 11th Nov 2016
20 | 3D change to be implemented by Raju and share with Team. | 1 |  | Requirement finalized on 10th Nov 2016 | InProgress | Completed and moved to live site. | 14th Nov 2016
21 | Headings to be made outline / more beautiful | 1 |  | Requirement finalized on 11th Nov 2016 | Templates sent Jeff. Awaiting for approval. | Completed and moved to live site.
22 | Basic Search : all module search headings : beautification along-with icon as discussed | 1 |  | Requirement finalized on 10th Nov 2016 | InProgress | Completed and moved to live site. | 22nd Nov 2016
25 | Company Logos : High Resolution Images to be used. | 2 |  | Requirement finalized on 10th Nov 2016 |  | Completed and moved to live site. | 22nd Nov 2016
28 | Dropdown default values and place holder/tooltip in the textbox controls in all search modules. | 1 |  |  |  | Will be completed by 29th Nov 2016 | 25th Nov 2016
27 | Company Signle View Performance issue fixing. | 1 |  | Modyfying the functionality and will show some progress on 25th Nov 2016 |  | Completed and moved to live site on 28th Nov 2016
29 | Admin panel for handling users and search history | 2 |  | Developing new admin panel to show new users, edit user profile and providing user access. |  |  | 25th Nov 2016
31 | Active Ingredient popup and chemical properties rearrangement | 1 |  | There is a bug in the current functionality. When multiple AIs exist for a product, we are showing only one AI. This issue is fixed and showing hyperlink on the AI name and when user clicks on the link showing the corresponding structure in a popup. |  | Development is completed, internal testing is in progress | 25th Nov 2016
32 | New page integration for Contact Us | 2 |  | Providing mail feature in the Contact Us page. |  | Completed. Integrated SendGrid SMTP API | 25th Nov 2016
33 | Patent Pdf linking from Shared path | 1 |  | InProgress |  | Completed on 29th Nov 2016 | 29th Nov 2016
37 | Pdf Header with url and logo | 2 |  |  |  | Completed on 30th Nov 2016
41 | Watermark in pdf and whitepapers | 2
42 | Enable/Disable modules in company single view | 1 |  |  |  | Completed on 5th Dec 2016 | 5th Dec 2016
34 | Blog UI Changes | 2 |  | In progress |  | Completed on2nd Dec 2016 | 2nd Dec 2016
39 | White papers integration | 1 |  |  |  |  | 2nd Dec 2016
3 | Back button functionality | 2 | 11th Nov 2016 |  |  |  | 2nd Dec 2016
46 | Include Flyer in Pdf Export | 1 |  | Completed
50 | Include Footer section in Pdf Export. | 1 |  | Completed |  |  | 8th Dec 2016

## Team Leaves
S.No | Name | Planned leaves for Dec End 2016 and Jan 2017
1 | Ramya | 28th Dec 2016
2 | Swetha | 12th & 27th Jan 2017
3 | Sireesha | 16th, 17th and 27th Jan 2017
4 | Purna | 16th Jan 2017 and Paternity leaves
5 | Siva | 12th & 16th Jan 2017
6 | Raju | No leaves
7 | Sharad | 2nd Jan to 6th Jan 2017
8 | Srikanth | 30th Dec 2016 and 27th Jan 2017
9 | Sairam | No Leaves
10 | Prasad | 12th, 16th and 17th Jan 2017
11 | Rajesh | 12th Jan 2017. 16th Jan 2017 (Work from Home)